## Slide 1: Surveillance Technology Working Group Meeting #8 8.10.2021

## Slide 2: Agenda
Where We Are
Review
New Request
Comments Received
Audit
Documentation
Next Steps
Questions

## Slide 3: Where we are
Review Press Release and other documentation
Last session
Today
Coming up
Move forward on assessing FotoKite and Vacant Lot Monitoring
Recommendation on FotoKite, vote on COPS cameras

## Slide 4: Review
Decisions
Fotokite: Aerial UAS allowing for different perspectives during crisis response. Not exempt, will go through the process.
  Press Release out, done with public comment period
  Public comments received, received comments from SPD
Vacant Lot Monitoring: Sensor that detect changes in a scene to monitor lots for dumping. Not exempt, will go through the process.
  Press Release out, done with public comment period
  Public comments received, waiting for updated data from
Community Asset Tracker: Camera with machine learning algorithm to identify objects within the city. Not enough information, tabled until more details are provided.
  Assessed last week, documentation provided

## Slide 5: Review
SLAs
2 - 6 Weeks
(10 - 30
Business Days)
Initial submission to determination of surveillance
Every 2 Weeks
(10 Business Days)
Short duration meeting to vote on technology exemptions
2 Weeks
(10 Business Days)
Public comment period:
Issuance of press release
Council meeting
(*) For now public input will be received via a Google Form and in the future will be on the new website.
2 Weeks
(10 Business Days)
Submission of finalized form (by dept.) to time of recommendation.
Group will individually research; departments will get follow-up questions; group to vote yes/no; and submit recommendation.
Notes: Ask that every member of the team complete the Google Form for both technologies
Collect form responses
Then we would send to sender
Then they would respond to the feedback
Then they would send a response
Then we review and vote (decide how we will vote)

## Slide 6: New Request
COPS Cameras
Surveillance cameras installed on telephone poles located on the City of Syracuse Streets.
Cameras use a secure network of fiber and air fiber lines that come back to a secure server where the video is kept for 30 days.
Purpose: to enhance public safety, assist in the deterrence and investigation of crime, and protect critical infrastructure of the Syracuse Police Department (SPD) and the City of Syracuse (City), through the use of cameras connected the Genetec Video System.

## Slide 7: Comments Received
FotoKite
Updated comments sent in pre-meeting email.
Vote on recommendation needs to be completed next meeting
Two volunteers will be needed to write the affirming and dissenting statements to provide to the Mayor

## Slide 8: Audit
Technology Audit
Technologies already implemented need to be audited and documented by the working group
**Please also send any technologies that you are aware of over to Amanda to be documented for the technology audit**

## Slide 9: Documentation
Open Data Portal: Surveillance Technology
All slide decks
Cleaned, summary notes
Process map & SLAs
One pager: https://www.canva.com/design/DAEedxSFoew/5RUaAet4DVxvzUko8i-p5A/edit
Definitions
Technology audit
Eventually… Working Group recommendations to the Mayor

## Slide 10: Next Steps
Next Steps
Check in with stakeholders of Vacant Lot Monitoring
Vote on recommending FotoKite
More forward with new request
  Inform of exemption
  OR put out for public comment period
Publish documentation
Continue building audit

## Slide 11: Questions
?